SPATIAL PLANNING AND INFRASTRUCTURE PARTNERSHIP
WORK PROGRAMME AND MEETINGS FORWARD PLAN

	Task/Issue
	Responsibility
	Target meeting for decision

	Consultation arrangements
	Notes

	1.

SPIP Terms of Reference / Work Programme and Forward Plan for Meetings / staff support 


	CDC as initial lead authority
	Inception meeting 20.08.09

T o R Finalised Meeting 1

09.12.09

Meeting 5
28.06.10
Staff support


	
	Papers circulated 11.08.09

T o R Circulated with Notes of Meeting 1 09.12.09

Long term staff support outstanding until allocation of LLA funding (see 2 below)


	2.

Proposals for use of LAA 2 reward grant allocated to Oxfordshire Housing Partnership 
	VOWH DC (for OHP) will prepare report
	Meeting 5
28.06.10
	Preparation by OHP networks
	This will include proposals for funding of co-ordinating officer for OHP/SPIP.  Other additional projects to consider.



	3.

HCA Single Conversation Inception 
	CDC / HCA
	Inception meeting 20.08.09


	
	Papers circulated by HCA in initial LA meetings

Initial ideas for Investment Plan priorities agreed 
 

	4.

HCA Single Conversation Local Investment Plan (LIP) and Agreement (LIA)

	CDC / HCA
	Meeting 1
09.12.09
Meeting 2

02.02.10

Meeting 3

01.03.10

Meeting 4

22.04.10

Meeting 5
28.06.10

	Wider partnership members invited to contribute on basis of work in progress
Delegation to LA leaders to consider emerging prioritisation


	Work in progress endorsed (Working Paper 5)
Meeting 2 to agree LIP draft

Meeting 3/4 to agree final LIP and consider approach to LIA
Meeting 5 to agree LIA. Includes process update from HCA


	5.

Economic Assessment commissioning


	OCC
	Meeting 3

01.03.10


	
	Organisational and issues update, background information, endorsement



	6.

Economic Development Strategy and delivery advice to LAs, PSB and  OEP (for Business Plan).  (Includes priorities for use of LLA reward grant in this field)


	CDC/OCC
	Meeting 5
28.06.10


	OEP 
	Economic Development Update:
· Economic assessment

· Commissioning of Strategy refresh

· LAA Funding from Economic Development



	7.

Evidence and advice to LPAs and County Council on initial feedback to on Regional Planning Body on Review of SE Plan


	CDC 
	Meeting 1
09.12.09

Meeting 3
01.03.10

Meeting 4

22.04.10

Meeting 5

28.06.10


	
	Organisational and issues update and background information only at this stage

SEEPB presentation to Meeting 3

Original intention overtaken by change in government – agenda item to consider local responses. 


	8.

Infrastructure advice to LPAs and district LSPs for LDF Infrastructure Plans (Local Government functions)


	CDC / City /  OCC
	Unprogrammed

	Includes discussion of joint working protocols on planning agreement/CIL viability issues
(see 10 below)


	Possible outcome of Single Conversation work

	9.

Infrastructure advice to LPAs and district LSPs for LDF Infrastructure Plans (other providers)


	CDC / City / OCC
	Unprogrammed
	Includes discussion of joint working protocols on planning agreement/CIL viability issues

(see 10 below)

	Possible outcome of Single Conversation work

	10.

Information on future of Planning Agreements/ Community Infrastructure Levy
	CDC
	Meeting 3

1.3.10

Further consideration unprogrammed
	
	Request for information only, but possible implications for future arrangements to implement the intent of the Single Conversation work (see 8/9 above)


	11.

Local Transport Plan 3 – liaison and advice to Highway Authority


	OCC
	Meeting 1
08.12.09

Meeting 5
28.06.10
	Formal consultation procedures
	Organisational and issues update and background information only at this stage

Regular consideration anticipated



	12.

High Speed 2 Railway - liaison and advice to LAs on consultation responses


	CDC /OCC
	Meeting 1

09.12.09 

Further consideration awaiting launch of formal consultation

	Possible need for hosted meeting with affected Parish Councils and MPs
	Full update: HS2 to be invited

	13.

LAA Priorities:

New and affordable dwellings delivery progress and homelessness prevention response. Renegotiation of LAA Dwellings Targets

(Includes priorities for use of LAA reward grant and Supporting People funding in this field)


	VWHDC for OHP / GOSE
	Meeting 1
09.12.09

Meeting 3

01.03.10

Meeting 5

28.06.10
	Preparation via OHP networks
	LAA Targets initial response endorsed and submitted.  Follow up consideration likely at Meeting 5

	14.

LAA NPI Monitoring


	CDC / OCC
	Regular reporting cycle prior to PSB
	
	Outstanding – support required from County Partnership Unit



	15.

Flood Bill Arrangements
	OCC 
	Unprogrammed
	
	Transfer of responsibility



	16.

Oxfordshire Rural Housing Partnership


	OHP / ORHP
	Meeting 6
Date TBC
	
	First of annual reports

	17.

Oxon 2030 Refresh


	OCC
	Meeting 6

Date TBC


	
	Work delayed, but in progress with County Partnership Unit




Meeting Programme  

Inception:
20 August 2009

Meeting 1:
8 December 2009

Meeting 2:
2 February 2010 (additional to deal with single conversation workload)
Meeting 3:
1 March 2010
Meeting 4:
22 April 2010

Meeting 5:
28 June 2010  
Meeting 6:
Date TBC: will be August / September 2010 (handover of lead CDC to Oxfordshire 

             County Council)
Updated: 23-Jun-10
